## Description
SocialTalent Technical Deployment - High Level Project Plan Template
Note - Not all of the following requirements may be in scope. Customers should work with SocialTalent customer success representative to assess requirements
No. | Deliverables/Tasks | Details | Customer Actions | SocialTalent Actions | Persons Responsible | Due Date | Status
1 | Sandbox Enivornment is stood up. | If the customer is in pre launch, it is likely that a Sandbox environment will not be required. Usually just a small number of users are set up to use the Sandbox Environment.
1.1 | Assess requirements as to whether a Sandbox environment is required | Decision on need for Sandbox environment | Discuss with SocialTalent | Discuss and assist with decision making
1.2 | Setup company admin user(s) | Company admin users are setup manually by SocialTalent. Typically, no more than 2 or 3 users would be set up as company adminswould be set up | Share details with Customer Success names and email addresses of users that may be company admins | Customer Success setup company admin users, assign learning path regarding Platform Administration
1.3 | Plaform Administration learning completed by Company Admins | Company Admins are required to complete Platform Administration training. Company Admins need to have a sufficient understanding of how the platform works. This is essential to success of the deployment and on going operation of the platform | Project Manager nudges Company Admins to complete the Platform Administration training | Assist when questions regarding the training arise
1.4 | Learners and Team Leader setup | Learners and Team Leaders have been set up, depending on the numbers this may be done manually (one-by-one) or through the use of the bulk-uploader. | Load users | Assist when questions regarding the training arise.
2 | Production Enivornment is setup. | Production Enivornment is stood up with (at a min.) the first batch of users on boarded.
2.1 | Setup company admin user(s) | Company admin users are setup manually by SocialTalent. Typically, no more than 2 or 3 users would be set up as company adminswould be set up | Share details with Customer Success names and email addresses of users that may be company admins | Customer Success setup company admin users, assign learning path regarding Platform Administration
2.2 | Plaform Administration learning completed by Company Admins | If there is no Sandbox environemnt this step is necessary. Company Admins are required to complete Platform Administration training. Company Admins need to have a sufficient understanding of how the platform works. This is essential to success of the deployment and on going operation of the platform | Project Manager nudges Company Admins to complete the Platform Administration training | Assist when questions regarding the training arise
2.3 | Test user access for a few users | Ideally the test users should be from different teams, groups, countries and IT organisations. Users should also engage in system testing using the following link https://app.socialtalent.com/test | Identifiy a few users and share the details with SocialTalent for loading | Customer success to set up the selected users
2.4 | Learners and Team Leader setup | Learners and Team Leaders have been set up, depending on the numbers this may be done manually (one-by-one) or through the use of the bulk uploader. | Load users | Assist when questions regarding the training arise
3 | Single Sign-on (SSO) | SSO is enabled. Users may log in via SSO
3.1 | Review SocialTalent SSO Documentation on this knowledge base article | Documentation has been reviewed | Review documentation | Promptly address questions as the arise
3.2 | SSO configuration details are populated | Per knowledge base article, populate details regarding configuration of SSO | Populate SSO details | Promptly address questions as the arise
3.3 | SSO is validated and tested | An email is sent to the team validating that SSO has be set up and is working | Test SSO | Promptly address questions as the arise
3.4 | Exclude certain users from SSO. | On occasion, some users may need to be exluded from SSO. Theses need to be defined and configured. | Exclude users | Promptly address questions as the arise
3.5 | Indentify Employee ID in SAML string | On occasion, the customer might want the employee id field to be passed from the SAML string and populated in a custom field on SocialTalent | Specify the location of the employee ID in SAML | Map the employee ID value from SAML to a custom ID field
4 | SSO Auto Provisioning (Self-registration) | Users may self-register/auto provision. This is an optional step. The bulk-uploader may be used as an alternative to auto provisioning.
4.1 | Trusted Domains have been configured | Email domains relating to all users have been defined and configured. Only users with emails will be permitted to self register. | Communicated trusted domains to SocialTalent. | Configure the trusted domains
4.2 | Configure trunk questions and teams | When users log in the team they are assigned to may need to have learning paths assigned by default. | Confer with SocialTalent and share details re the Learning paths that should be assigned based on Trunk questions and teams | Configure trunk teams
4.3 | If necessary, configure Branch Questions and Branch Teams | Depending on the complexity of the question structure, they may need to be forked to create branch teams | Confer with SocialTalent and share details re the Learning paths that should be assigned based on Branch questions and teams | Configure branch teams
4.4 | Restrict reporting and data analysis for users of particular countries. | There are cases where the personal data from users that live in some countries may need to be restricted e.g. it may be the case that users based in Germany have exposure to their learning progress restricted. | Confer with SocialTalent and share details re requirements for data restrictions | Configure data restrictions for countries
4.5 | Test and validate Auto provisioning | Users need to be able to register and authenticate via SSO and be assigned to the correct teams and learning paths. | Execute test | Assist in validating tests
5 | User Auto Provisioning API setup (SCIM) | Instead of bulk update or self-registration, the customer can choose to use SCIM API, which automated user management | SCIM Overview Document
5.1 | Share understanding of SCIM with Customer PM and Customer tech team | Discuss what SCIM is, how would it solve their problems, how could it impact existing users if any. Decisions about should company admins continue to be allowed to make changes etc. |  | Share documentation, answer any questions.
5.2 | Share credentials to the SCIM API endpoint. | This could be for production or sandbox environment, depending on customer's comfort level with SCIM and status of production roll-out. |  | Create sandbox company, create admin@company.com account, create and share the API security token and documentation.
5.3 | Configure and integrate SCIM. | This integration could be done with customer Identity Management systems like Azure or Okta, or in some cases LMSs like Workday as well. | Integration tasks. | Answer any queries arising in the process.
5.4 | Test, test, test. Integration testing for the API. | 1. Deactivation. 2. If changes made by company admins are over-written. 3. What happens to existing users, are their attributes over-written. | Run test cases. | Assist in validating test results.
5.5 | Incrementally add users to SCIM | If for example there are 10k users, add 100 users first, to see how their experience is and if there are any issues. | IDP admin to incrementally add users.
6 | File Content Integration | Assess intergation options | Review high level integation capabilities in this document | Customer Success rep to arrange a meeting with Product Development as necessary
6.1 | Content File Formats | The format of the Content File(s) needs to be defined: a) Field names, lengths, required status b) Field mapping c) File name | Review this document for sample data fields and other details | Export content data in a file that conforms to the Completion File requirements
6.2 | Test and iterate on Content Files until validated | Content files will need to undergo riogorous testing to ensure they are consistent with requirements | Test content file uploads and share feedback re testing | Address any requirements for iteration.
6.3 | Completion File Formats | The format of the Completion File needs to be defined: a) Field names, lengths, required status b) Field mapping c) File name | Communicate Completion File requirements in detail | Export content data in a file that conforms to the Completion File requirements
6.4 | Test and iterate on Content Files until validated | Content files will need to undergo riogorous testing to ensure they are consistent with requirements | Test content file uploads and share feedback re testing | Address any requirements for iteration.
6.5 | SFTP Server Setup | Customer needs to setup an SFTP server as the location as to where the Content and Completion files will reside. | Share with SocialTalent a) IP Address of SFTP server b) Authentication details c) White listing of SocialTalent IPs | Export Content and Completion files to SFTP Server.
Optional Deliverable
Mandatory Deliverable

## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE
Enter Company Name in cell B2. | Company Name
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead | Project Start: |  | 2022-11-01
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-10-31 to 2022-12-25
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | PERSON RESPONSIBLE | PROGRESS | START | END | DAYS | time axis 2022-10-31 to 2022-12-25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Production Enivornment is setup.
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Setup company admin user(s) | Name | 50% | 2022-11-01 | 2022-11-04 | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Plaform Administration learning completed |  | 60% | 2022-11-04 | 2022-11-06 | 3
| Test user access for a few users |  | 50% | 2022-11-06 | 2022-11-10 | 5
| Learners and Team Leader setup | ME | 100% | 2022-11-10 | 2022-11-14
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Single Sign-on (SSO)
| Review SocialTalent SSO Documentation |  | 50% | 2022-11-15 | 2022-11-19 | 5
| SSO configuration details are populated |  | 50% | 2022-11-17 | 2022-11-22 | 6
| SSO is validated and tested |  |  | 2022-11-22 | 2022-11-25 | 4
| Exclude certain users from SSO. |  |  | 2022-11-22 | 2022-11-24 | 3
| Indentify Employee ID in SAML string |  |  | 2022-11-22 | 2022-11-25 | 4
Sample phase title block | SSO Auto Provisioning (Self-registration)
| Trusted Domains have been configured |  |  | 2022-11-16 | 2022-11-21 | 6
| Configure trunk questions and teams |  |  | 2022-11-22 | 2022-11-26 | 5
| If necessary, configure Branch Questions and Branch Teams |  |  | 2022-11-27 | 2022-12-02 | 6
| Restrict reporting and data analysis for users of particular countries. |  |  | 2022-12-03 | 2022-12-07 | 5
| Test and validate Auto provisioning |  |  | 2022-11-27 | 2022-12-01 | 5
Sample phase title block | User Auto Provisioning API setup (SCIM)
| Share understanding of SCIM with Customer PM and Customer tech team |  |  | 2022-12-02 | 2022-12-07 | 6
| Share credentials to the SCIM API endpoint. |  |  | 2022-12-08 | 2022-12-12 | 5
| Configure and integrate SCIM. |  |  | 2022-12-13 | 2022-12-18 | 6
| Test, test, test. Integration testing for the API. |  |  | 2022-12-13 | 2022-12-17
| Incrementally add users to SCIM |  |  | 2022-12-13 | 2022-12-17 | 5
Sample phase title block | File Content Integration
| Content File Formats |  |  | 2022-12-01 | 2022-12-06 | 6
| Test and interate on Content Files until validated |  |  | 2022-12-07 | 2022-12-11 | 5
| Completion File Formats |  |  | 2022-12-12 | 2022-12-17 | 6
| Test and interate on Content Files until validated |  |  | 2022-12-18 | 2022-12-22 | 5
| SFTP Server Setup |  |  | 2022-12-12 | 2022-12-16 | 5
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one